## Sprint Planning
Epic | User Story ID | Feature/TItle | User Story | Story Points | Sprint | Labels
Create a web-based platform to educate and engage users about the Agile Manifesto and methodologies | US001 | Home page for Agile Manifesto | I want to design and implement a visually appealing homepage that captures user attention. I want to use a clean, modern layout with intuitive navigation, responsive design, and high-quality visuals. I also want to incorporate a compelling hero section with a clear call-to-action, engaging content, and consistent branding while ensuring fast loading times and accessibility. | 8 | 1 | AgilePlatform
| US002 | Agile Values and Principles | I want to create a visually appealing page for the four core Agile values, using a clean layout, intuitive navigation, responsive design, and high-quality visuals. Each value will have a dedicated section with concise explanations and supporting graphics. I’ll ensure fast loading, accessibility, and consistent branding for an engaging user experience. | 5 | 2 | AgilePlatform
| US003 | Resource Library | I want to design a visually appealing library for Agile practices like Scrum, Kanban, and others. The library will have a clean layout, intuitive navigation, responsive design, and high-quality visuals. Each Agile practice will have a dedicated section with detailed explanations, diagrams, and resources. I’ll ensure fast loading, accessibility, and consistent branding to create an engaging and informative user experience. | 3 | 3 | AgilePlatform
| US004 | Collabortaion Features | I want to develop a visually appealing discussion forum for users, featuring a clean, modern layout, intuitive navigation, responsive design, and high-quality visuals. The forum will include categories for different topics, user profiles, and interactive features like posting, replying, and liking. I'll ensure fast loading times, accessibility, and consistent branding for an engaging user experience. | 8 | 4 | AgilePlatform
| US005 | Collabortaion Features | I want to enable users to comment on resources and principles with an easy-to-use interface. The design will include comment sections under each resource or principle, allowing users to post, reply, and like comments. I'll ensure a clean layout, responsive design, and intuitive navigation for a smooth experience. Fast loading, accessibility, and consistent branding will enhance the overall user experience. | 8 | 5 | AgilePlatform
JIra Project Link | https://balajiyoganantham4.atlassian.net/jira/software/projects/SCRUM/boards/1/timeline?shared=&atlOrigin=eyJpIjoiYmVmNTM4YmU2MzcxNDNkZTgyMmJlYjg2YTYwNWRlZTEiLCJwIjoiaiJ9